## Instructions
COST-BENEFIT ANALYSIS CALCULATOR
Calculates NPV, benefit-cost ratio, IRR, payback, sensitivity and switching values for a project or option.
1. Inputs | Enter the project name, currency, Year 0, analysis period (max 20 years), discount rate and residual value. Yellow cells are key assumptions – document the source of each.
2. Costs | Section A: recurring costs (annual amount, start and end year, real escalation). Section B: one-off or irregular costs typed directly under each year (e.g. construction in Years 0–1, replacements).
3. Benefits | Same structure as Costs. Express all benefits in money terms (revenue, savings, valued time or health gains).
4. Results | Shows the discounted cash flow by year and the key indicators: PV of benefits and costs, NPV, BCR, IRR, simple and discounted payback, and the decision rule.
5. Sensitivity | Tests how results change if costs, benefits or the discount rate change; shows switching values and an NPV profile. Edit the custom scenario as needed.
6. Summary | One-page overview with key indicators, decision, robustness checks and charts – ready to paste into reports.
Decision rules | Accept if NPV > 0 and BCR > 1 (IRR above the discount rate). When comparing options, prefer the one with the highest NPV.
Example data | The water-supply example figures are illustrative only. Replace them with your project data.
Colour key
Blue text | Inputs you can change.
Black text | Calculations – do not overwrite.
Green text | Links pulled from another sheet.
Yellow fill | Key assumptions and headline results.
Conventions | Constant (real) prices with a real discount rate; end-of-year discounting with Year 0 undiscounted; flows after the analysis period are excluded.

## Inputs
INPUTS AND ASSUMPTIONS
Blue = input. Yellow fill = key assumptions that drive the results. All amounts in constant (real) prices unless stated.
Assumption | Value | Notes / source
Project / option name | [Community Water Supply Scheme – Option A] | Name shown on all outputs
Analyst / prepared by | [Name]
Currency | GHS | All amounts in this currency
First year of analysis (Year 0) | 2027 | Calendar year of Year 0 – usually the year of initial investment
Analysis period (years after Year 0) | 15 | Maximum 20 years; typically the economic life of the main assets
Discount rate (real, % per year) | 10% | Use the official / social discount rate required by your organisation, government or funder
Residual value at end of period | 100000 | Remaining value of assets at the end of the analysis period (added as a benefit in the final year)
Sensitivity step (±%) | 20% | Used for the standard cost and benefit sensitivity scenarios
Alternative discount rate – low | 6% | For sensitivity testing
Alternative discount rate – high | 14% | For sensitivity testing
Cost and benefit categories (for drop-downs)
Cost categories | Benefit categories
Capital / investment | Revenue / income
Operating | Cost savings
Maintenance | Time savings
Staff / personnel | Health benefits
Social / environmental cost | Environmental benefits
Other | Other
Note on B10: Example value only. Replace with the discount rate required by your organisation or funder, and cite the source in column C.
Note on B11: Example value only – estimate from asset register or engineering advice.

## Costs
COSTS SCHEDULE
[Community Water Supply Scheme – Option A] ¦ GHS, constant prices
Section A: recurring items – enter annual amount, start/end year and real escalation (blue); yearly values calculate. Section B: one-off or irregular items – type amounts directly under each year.
Item | Category | Annual amount | Start year | End year | Escalation % p.a. (real) | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
[5 empty] | Calendar year → | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
A. Recurring items
Operation and staff costs | Staff / personnel | 40000 | 1 | 15 | 0% | 0 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 0 | 0 | 0 | 0 | 0
Maintenance and repairs | Maintenance | 15000 | 1 | 15 | 2% | 0 | 15000 | 15300 | 15606 | 15918.12 | 16236.4824 | 16561.212 | 16892.4363 | 17230.285 | 17574.8907 | 17926.3885 | 18284.9163 | 18650.6146 | 19023.6269 | 19404.0995 | 19792.1814 | 0 | 0 | 0 | 0 | 0
Water treatment chemicals and energy | Operating | 12000 | 1 | 15 | 1% | 0 | 12000 | 12120 | 12241.2 | 12363.612 | 12487.2481 | 12612.1206 | 12738.2418 | 12865.6242 | 12994.2805 | 13124.2233 | 13255.4655 | 13388.0202 | 13521.9004 | 13657.1194 | 13793.6906 | 0 | 0 | 0 | 0 | 0
Monitoring and evaluation | Other | 5000 | 1 | 15 | 0% | 0 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal A | [5 empty] | 0 | 72000 | 72420 | 72847.2 | 73281.732 | 73723.7305 | 74173.3326 | 74630.6781 | 75095.9092 | 75569.1712 | 76050.6118 | 76540.3818 | 77038.6348 | 77545.5273 | 78061.2188 | 78585.872 | 0 | 0 | 0 | 0 | 0
B. One-off / irregular items (enter amounts under each year)
Construction of intake, tank and pipeline | Capital / investment |  |  |  |  | Year 0 2027: 600000; Year 1 2028: 150000
Design, supervision and permits | Capital / investment |  |  |  |  | Year 0 2027: 60000
Pump and equipment replacement | Capital / investment |  |  |  |  | Year 8 2035: 80000
Community mobilisation and training | Operating |  |  |  |  | Year 0 2027: 20000; Year 1 2028: 10000
Subtotal B | [5 empty] | 680000 | 160000 | 0 | 0 | 0 | 0 | 0 | 0 | 80000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COSTS |  |  |  |  | 2047564.0002 | 680000 | 232000 | 72420 | 72847.2 | 73281.732 | 73723.7305 | 74173.3326 | 74630.6781 | 155095.9092 | 75569.1712 | 76050.6118 | 76540.3818 | 77038.6348 | 77545.5273 | 78061.2188 | 78585.872 | 0 | 0 | 0 | 0 | 0
Costs by category (undiscounted, within analysis period)
Capital / investment | 890000
Operating | 223162.7464
Maintenance | 259401.2537
Staff / personnel | 600000
Social / environmental cost | 0
Other | 75000
Note on F48: Undiscounted total over all 21 year columns (Results applies the analysis period).

## Benefits
BENEFITS SCHEDULE
[Community Water Supply Scheme – Option A] ¦ GHS, constant prices
Section A: recurring items – enter annual amount, start/end year and real escalation (blue); yearly values calculate. Section B: one-off or irregular items – type amounts directly under each year.
Item | Category | Annual amount | Start year | End year | Escalation % p.a. (real) | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20
[5 empty] | Calendar year → | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
A. Recurring items
Water user fees (revenue) | Revenue / income | 60000 | 1 | 15 | 3% | 0 | 60000 | 61800 | 63654 | 65563.62 | 67530.5286 | 69556.4445 | 71643.1378 | 73792.4319 | 76006.2049 | 78286.391 | 80634.9828 | 83054.0322 | 85545.6532 | 88112.0228 | 90755.3835 | 0 | 0 | 0 | 0 | 0
Time saved collecting water (valued) | Time savings | 90000 | 2 | 15 | 2% | 0 | 0 | 90000 | 91800 | 93636 | 95508.72 | 97418.8944 | 99367.2723 | 101354.6177 | 103381.7101 | 105449.3443 | 107558.3312 | 109709.4978 | 111903.6878 | 114141.7615 | 116424.5967 | 0 | 0 | 0 | 0 | 0
Reduced household health costs | Health benefits | 70000 | 2 | 15 | 2% | 0 | 0 | 70000 | 71400 | 72828 | 74284.56 | 75770.2512 | 77285.6562 | 78831.3693 | 80407.9967 | 82016.1567 | 83656.4798 | 85329.6094 | 87036.2016 | 88776.9256 | 90552.4641 | 0 | 0 | 0 | 0 | 0
Avoided costs of buying water | Cost savings | 25000 | 1 | 15 | 0% | 0 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subtotal A | [5 empty] | 0 | 85000 | 246800 | 251854 | 257027.62 | 262323.8086 | 267745.5901 | 273296.0663 | 278978.419 | 284795.9117 | 290751.892 | 296849.7937 | 303093.1394 | 309485.5426 | 316030.7099 | 322732.4444 | 0 | 0 | 0 | 0 | 0
B. One-off / irregular items (enter amounts under each year)
Salvage of old equipment | Other |  |  |  |  | Year 9 2036: 8000
Subtotal B | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL BENEFITS |  |  |  |  | 4054764.9377 | 0 | 85000 | 246800 | 251854 | 257027.62 | 262323.8086 | 267745.5901 | 273296.0663 | 278978.419 | 292795.9117 | 290751.892 | 296849.7937 | 303093.1394 | 309485.5426 | 316030.7099 | 322732.4444 | 0 | 0 | 0 | 0 | 0
Benefits by category (undiscounted, within analysis period)
Revenue / income | 1115934.8332
Cost savings | 375000
Time savings | 1437654.4338
Health benefits | 1118175.6707
Environmental benefits | 0
Other | 8000
Note on F48: Undiscounted total over all 21 year columns (Results applies the analysis period).

## Results
RESULTS – DISCOUNTED CASH FLOW
[Community Water Supply Scheme – Option A] ¦ GHS, constant prices ¦ Discount rate: 10.0% ¦ Period: 15 years
Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Calendar year | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
In analysis period (1 = yes) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Benefits | 0 | 85000 | 246800 | 251854 | 257027.62 | 262323.8086 | 267745.5901 | 273296.0663 | 278978.419 | 292795.9117 | 290751.892 | 296849.7937 | 303093.1394 | 309485.5426 | 316030.7099 | 322732.4444 | 0 | 0 | 0 | 0 | 0
Residual value | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 0 | 0 | 0 | 0 | 0
Total benefits | 0 | 85000 | 246800 | 251854 | 257027.62 | 262323.8086 | 267745.5901 | 273296.0663 | 278978.419 | 292795.9117 | 290751.892 | 296849.7937 | 303093.1394 | 309485.5426 | 316030.7099 | 422732.4444 | 0 | 0 | 0 | 0 | 0
Total costs | 680000 | 232000 | 72420 | 72847.2 | 73281.732 | 73723.7305 | 74173.3326 | 74630.6781 | 155095.9092 | 75569.1712 | 76050.6118 | 76540.3818 | 77038.6348 | 77545.5273 | 78061.2188 | 78585.872 | 0 | 0 | 0 | 0 | 0
Net benefit (benefits – costs) | -680000 | -147000 | 174380 | 179006.8 | 183745.888 | 188600.0781 | 193572.2574 | 198665.3882 | 123882.5098 | 217226.7405 | 214701.2802 | 220309.4119 | 226054.5047 | 231940.0153 | 237969.4911 | 344146.5724 | 0 | 0 | 0 | 0 | 0
Cumulative net benefit | -680000 | -827000 | -652620 | -473613.2 | -289867.312 | -101267.2339 | 92305.0235 | 290970.4117 | 414852.9215 | 632079.662 | 846780.9422 | 1067090.3541 | 1293144.8588 | 1525084.874 | 1763054.3652 | 2107200.9375 | 2107200.9375 | 2107200.9375 | 2107200.9375 | 2107200.9375 | 2107200.9375
Discount factor | 1 | 0.90909 | 0.82645 | 0.75131 | 0.68301 | 0.62092 | 0.56447 | 0.51316 | 0.46651 | 0.4241 | 0.38554 | 0.35049 | 0.31863 | 0.28966 | 0.26333 | 0.23939 | 0.21763 | 0.19784 | 0.17986 | 0.16351 | 0.14864
PV of benefits | 0 | 77272.7273 | 203966.9421 | 189221.6379 | 175553.3229 | 162882.4463 | 151135.4055 | 140244.0951 | 130145.4914 | 124174.0488 | 112097.4408 | 104044.0418 | 96574.8149 | 89646.9377 | 83220.7632 | 101198.7862 | 0 | 0 | 0 | 0 | 0
PV of costs | 680000 | 210909.0909 | 59851.2397 | 54731.1796 | 50052.409 | 45776.6363 | 41868.9126 | 38297.3383 | 72353.3863 | 32048.7055 | 29320.803 | 26826.9369 | 24546.8832 | 22462.1771 | 20555.9587 | 18812.833 | 0 | 0 | 0 | 0 | 0
PV of net benefit | -680000 | -133636.3636 | 144115.7025 | 134490.4583 | 125500.9139 | 117105.81 | 109266.4929 | 101946.7568 | 57792.1051 | 92125.3433 | 82776.6378 | 77217.1049 | 72027.9317 | 67184.7607 | 62664.8046 | 82385.9532 | 0 | 0 | 0 | 0 | 0
Cumulative PV of net benefit | -680000 | -813636.3636 | -669520.6612 | -535030.2029 | -409529.289 | -292423.479 | -183156.9861 | -81210.2293 | -23418.1242 | 68707.2191 | 151483.8569 | 228700.9618 | 300728.8934 | 367913.6541 | 430578.4587 | 512964.4119 | 512964.4119 | 512964.4119 | 512964.4119 | 512964.4119 | 512964.4119
Payback flag (helper) | 6 2033: 6
Discounted payback flag (helper) | 9 2036: 9
KEY INDICATORS
Indicator | 0 2027: Value
Present value of benefits (PVB) | 0 2027: 1941378.9019
Present value of costs (PVC) | 0 2027: 1428414.49
Net present value (NPV = PVB – PVC) | 0 2027: 512964.4119
Benefit-cost ratio (BCR = PVB ÷ PVC) | 0 2027: 1.3591
Internal rate of return (IRR) | 0 2027: 18.23%
Simple payback (years from Year 0) | 0 2027: 6
Discounted payback (years from Year 0) | 0 2027: 9
Equivalent annual net benefit | 0 2027: 67441.3686
Decision (NPV > 0 and BCR > 1) | 0 2027: Economically viable – proceed
Notes: Year 0 flows are not discounted (end-of-year convention). IRR uses the net benefit stream; 'n/a' means it cannot be calculated (e.g. no sign change). Equivalent annual net benefit spreads the NPV evenly over the period.

## Sensitivity
SENSITIVITY AND SCENARIO ANALYSIS
[Community Water Supply Scheme – Option A] ¦ Base discount rate 10.0%
Scenarios change benefits, costs or the discount rate. Edit the multipliers (blue) to define your own scenarios.
Scenario | Benefits × | Costs × | Discount rate | NPV | BCR | IRR | Result
Base case | 1 | 1 | 10% | 512964.4119 | 1.3591 | 18.23% | Viable
Costs higher (+ step) | 1 | 1.2 | 10% | 227281.5139 | 1.1326 | 13.23% | Viable
Costs lower (– step) | 1 | 0.8 | 10% | 798647.3099 | 1.6989 | 24.96% | Viable
Benefits lower (– step) | 0.8 | 1 | 10% | 124688.6315 | 1.0873 | 12.16% | Viable
Benefits higher (+ step) | 1.2 | 1 | 10% | 901240.1923 | 1.6309 | 23.67% | Viable
Worst case (costs +, benefits –) | 0.8 | 1.2 | 10% | -160994.2665 | 0.90608 | 7.512% | Not viable
Low discount rate | 1 | 1 | 6% | 954062.5168 | 1.5939 | 18.23% | Viable
High discount rate | 1 | 1 | 14% | 216024.3135 | 1.1657 | 18.23% | Viable
[Custom scenario] | 0.9 | 1.1 | 10% | 175985.0727 | 1.112 | 12.75% | Viable
Switching values
Increase in costs that would make NPV = 0 |  |  |  | 35.91%
Decrease in benefits that would make NPV = 0 |  |  |  | 26.42%
Interpretation: the larger the switching value, the more robust the result. Values below about 10–20% suggest high risk.
NPV at different discount rates
Discount rate |  |  |  | NPV
2% |  |  |  | 1631994.9831
5% |  |  |  | 1096478.9415
8% |  |  |  | 710906.8544
11% |  |  |  | 427800.5423
14% |  |  |  | 216024.3135
17% |  |  |  | 54796.1311
Helper: net benefit streams for scenario IRR (do not edit)
Base case | [5 empty] | -680000 | -147000 | 174380 | 179006.8 | 183745.888 | 188600.0781 | 193572.2574 | 198665.3882 | 123882.5098 | 217226.7405 | 214701.2802 | 220309.4119 | 226054.5047 | 231940.0153 | 237969.4911 | 344146.5724 | 0 | 0 | 0 | 0 | 0
Costs higher (+ step) | [5 empty] | -816000 | -193400 | 159896 | 164437.36 | 169089.5416 | 173855.332 | 178737.5909 | 183739.2526 | 92863.3279 | 202112.9063 | 199491.1578 | 205001.3356 | 210646.7777 | 216430.9098 | 222357.2474 | 328429.398 | 0 | 0 | 0 | 0 | 0
Costs lower (– step) | [5 empty] | -544000 | -100600 | 188864 | 193576.24 | 198402.2344 | 203344.8242 | 208406.9239 | 213591.5238 | 154901.6916 | 232340.5748 | 229911.4025 | 235617.4883 | 241462.2316 | 247449.1207 | 253581.7349 | 359863.7468 | 0 | 0 | 0 | 0 | 0
Benefits lower (– step) | [5 empty] | -680000 | -164000 | 125020 | 128636 | 132340.364 | 136135.3164 | 140023.1394 | 144006.1749 | 68086.826 | 158667.5582 | 156550.9018 | 160939.4532 | 165435.8768 | 170042.9068 | 174763.3491 | 259600.0835 | 0 | 0 | 0 | 0 | 0
Benefits higher (+ step) | [5 empty] | -680000 | -130000 | 223740 | 229377.6 | 235151.412 | 241064.8398 | 247121.3754 | 253324.6015 | 179678.1936 | 275785.9229 | 272851.6586 | 279679.3707 | 286673.1325 | 293837.1238 | 301175.6331 | 428693.0612 | 0 | 0 | 0 | 0 | 0
Worst case (costs +, benefits –) | [5 empty] | -816000 | -210400 | 110536 | 114066.56 | 117684.0176 | 121390.5703 | 125188.4729 | 129080.0393 | 37067.6441 | 143553.7239 | 141340.7794 | 145631.3768 | 150028.1498 | 154533.8013 | 159151.1054 | 243882.9091 | 0 | 0 | 0 | 0 | 0
Low discount rate | [5 empty] | -680000 | -147000 | 174380 | 179006.8 | 183745.888 | 188600.0781 | 193572.2574 | 198665.3882 | 123882.5098 | 217226.7405 | 214701.2802 | 220309.4119 | 226054.5047 | 231940.0153 | 237969.4911 | 344146.5724 | 0 | 0 | 0 | 0 | 0
High discount rate | [5 empty] | -680000 | -147000 | 174380 | 179006.8 | 183745.888 | 188600.0781 | 193572.2574 | 198665.3882 | 123882.5098 | 217226.7405 | 214701.2802 | 220309.4119 | 226054.5047 | 231940.0153 | 237969.4911 | 344146.5724 | 0 | 0 | 0 | 0 | 0
[Custom scenario] | [5 empty] | -748000 | -178700 | 142458 | 146536.68 | 150714.9528 | 154995.3242 | 159380.3651 | 163872.7138 | 80475.0769 | 180390.2322 | 178021.0298 | 182970.3944 | 188041.3272 | 193236.9083 | 198560.2982 | 294014.7407 | 0 | 0 | 0 | 0 | 0

## Summary
COST-BENEFIT ANALYSIS SUMMARY |  |  |  | Chart data (linked from Results)
[Community Water Supply Scheme – Option A] |  |  |  | Year | Benefits | Costs | Cumulative PV net
Prepared by [Name] ¦ GHS, constant prices ¦ Discount rate 10.0% ¦ 15 years from 2027 |  |  |  | 2027 | 0 | 680000 | -680000
|  |  |  | 2028 | 85000 | 232000 | -813636.3636
Net present value (NPV) | Benefit-cost ratio (BCR) |  | Internal rate of return (IRR) | 2029 | 246800 | 72420 | -669520.6612
512964.4119 | 1.3591 |  | 18.23% | 2030 | 251854 | 72847.2 | -535030.2029
|  |  |  | 2031 | 257027.62 | 73281.732 | -409529.289
PV of benefits | PV of costs |  | Discounted payback (years) | 2032 | 262323.8086 | 73723.7305 | -292423.479
1941378.9019 | 1428414.49 |  | 9 | 2033 | 267745.5901 | 74173.3326 | -183156.9861
|  |  |  | 2034 | 273296.0663 | 74630.6781 | -81210.2293
Economically viable – proceed |  |  |  | 2035 | 278978.419 | 155095.9092 | -23418.1242
|  |  |  | 2036 | 292795.9117 | 75569.1712 | 68707.2191
Robustness |  |  |  | 2037 | 290751.892 | 76050.6118 | 151483.8569
Switching value – costs |  | 35.91% |  | 2038 | 296849.7937 | 76540.3818 | 228700.9618
Switching value – benefits |  | 26.42% |  | 2039 | 303093.1394 | 77038.6348 | 300728.8934
Worst-case NPV (costs +, benefits –) |  | -160994.2665 |  | 2040 | 309485.5426 | 77545.5273 | 367913.6541
Scenarios with NPV > 0 |  | 8 of 9 |  | 2041 | 316030.7099 | 78061.2188 | 430578.4587
|  |  |  | 2042 | 422732.4444 | 78585.872 | 512964.4119
|  |  |  | 2043 | 0 | 0 | 512964.4119
|  |  |  | 2044 | 0 | 0 | 512964.4119
|  |  |  | 2045 | 0 | 0 | 512964.4119
|  |  |  | 2046 | 0 | 0 | 512964.4119
|  |  |  | 2047 | 0 | 0 | 512964.4119