## Instructions
PROJECT DELIVERABLES AND MILESTONE TRACKER
A simple tool to plan, track and report project deliverables and milestones.
1. Setup | Enter the project name, dates and amber warning period. Add your phases/workstreams and owners to the drop-down lists. The status date defaults to today.
2. Deliverables | List each deliverable with owner, dates, % complete, status and approval. Use 'Revised due' for agreed new dates; keep 'Planned due' as the baseline.
3. Milestones | List key milestones with baseline, forecast and actual dates, and link them to deliverables and payments or decision gates.
4. Dashboard | Review the summary: KPIs, status and RAG counts, progress by phase and next milestones. Use it in progress reports and meetings.
5. Timeline | View the automatic Gantt chart of deliverables by week.
6. Update regularly | Update % complete, status and dates weekly or before each progress meeting.
Example data | Rows D-01 to D-07 and M-01 to M-05 are examples showing how the tracker works. Overwrite or delete them.
RAG rules
Red | Not completed and past its due date (overdue).
Amber | Marked 'At risk', or due within the amber period (Setup) and less than 80% complete; for milestones, forecast later than baseline.
Green | On track.
Complete | Completed / achieved.
On hold | On hold or cancelled.
Colour key
Blue text | Cells you fill in. Black text on grey = calculated automatically; do not overwrite.

## Setup
PROJECT SETUP
Enter project details and edit the drop-down lists. Blue text on cream = editable.
Project name | [Project Name]
Project code | [PRJ-2026-001]
Sponsor / client | [Name / organisation]
Project manager | [Name]
Project start date | 2026-09-01
Project end date | 2027-02-26
Status date (report as at) | 2026-10-29
Amber warning (days before due) | 14
DROP-DOWN LISTS (add phases and owners in the cream cells)
|  | Deliverable status | Priority | Phase / workstream | Owners | Approval status | Milestone status
|  | Not started | High | Initiation | [Owner 1] | Not submitted | Not started
|  | In progress | Medium | Planning | [Owner 2] | Under review | On track
|  | At risk | Low | Execution | [Owner 3] | Approved | At risk
|  | On hold |  | Monitoring | [Owner 4] | Rejected | Achieved
|  | Completed |  | Closure | [Owner 5] |  | Missed
Cancelled
Note on B10: Defaults to today's date. Overwrite with a fixed date to report 'as at' a specific day.
Note on B11: Open items due within this many days and less than 80% complete are flagged Amber.

## Deliverables
PROJECT DELIVERABLES TRACKER
Project: [Project Name] ¦ Status date: 29-Oct-2026
Fill columns A–N (blue). Columns O–R calculate automatically. RAG: Red = overdue; Amber = at risk or due soon; Green = on track.
ID | Phase / workstream | Deliverable | Description / acceptance criteria | Owner | Priority | Planned start | Planned due | Revised due | Actual completion | % complete | Status | Approval | Dependencies | Effective due | Days to due | Slippage (days) | RAG | Comments / next steps
D-01 | Initiation | Project charter | Approved charter with scope, objectives and budget | [Owner 1] | High | 2026-09-01 | 2026-09-15 |  | 2026-09-14 | 100% | Completed | Approved |  | 2026-09-15 |  | -1 | Complete | Signed by sponsor
D-02 | Planning | Stakeholder engagement plan | Plan approved by steering committee | [Owner 2] | Medium | 2026-09-10 | 2026-09-30 |  | 2026-10-03 | 100% | Completed | Approved | D-01 | 2026-09-30 |  | 3 | Complete
D-03 | Planning | Baseline survey report | Final report with baseline values for all indicators | [Owner 3] | High | 2026-09-21 | 2026-10-23 |  |  | 70% | In progress | Not submitted | D-02 | 2026-10-23 | -6 | 0 | Red | Data cleaning delayed; draft due next week
D-04 | Execution | Procurement of equipment | Equipment delivered and inspected | [Owner 4] | High | 2026-10-05 | 2026-11-06 |  |  | 40% | In progress | Not submitted | D-01 | 2026-11-06 | 8 | 0 | Amber | Bids under evaluation
D-05 | Execution | Training of field staff | 40 staff trained; post-test ≥ 75% | [Owner 5] | Medium | 2026-11-16 | 2026-12-11 |  |  | 0% | Not started | Not submitted | D-04 | 2026-12-11 | 43 | 0 | Green
D-06 | Monitoring | Mid-term progress report | Report submitted to sponsor | [Owner 1] | Medium | 2026-12-14 | 2027-01-15 |  |  | 0% | Not started | Not submitted | D-03 | 2027-01-15 | 78 | 0 | Green
D-07 | Closure | Final evaluation report | Evaluation approved; lessons documented | [Owner 3] | High | 2027-01-18 | 2027-02-19 |  |  | 0% | Not started | Not submitted | D-06 | 2027-02-19 | 113 | 0 | Green
Formulas:
Effective due = IF([Planned due]="","",IF([Revised due]<>"",[Revised due],[Planned due]))

## Milestones
PROJECT MILESTONE TRACKER
Project: [Project Name] ¦ Status date: 29-Oct-2026
Fill columns A–J (blue). Columns K–N calculate automatically. Variance = forecast or actual date minus baseline (positive = late).
ID | Milestone | Phase / workstream | Linked deliverables | Owner | Baseline date | Forecast date | Actual date | Status | Payment / gate linked | Variance (days) | RAG | Effective date | Sort key | Comments
M-01 | Project launched | Initiation | D-01 | [Owner 1] | 2026-09-15 |  | 2026-09-16 | Achieved | Gate 1 | 1 | Complete | 2026-09-16 |  | Launch event held
M-02 | Baseline completed | Planning | D-03 | [Owner 3] | 2026-10-23 | 2026-11-06 |  | At risk |  | 14 | Amber | 2026-11-06 | 46332.0001 | Two-week delay forecast
M-03 | Equipment installed | Execution | D-04 | [Owner 4] | 2026-11-20 |  |  | On track | Payment 2 (30%) | 0 | Green | 2026-11-20 | 46346.0001
M-04 | Mid-term review | Monitoring | D-06 | [Owner 1] | 2027-01-22 |  |  | Not started | Gate 2 | 0 | Green | 2027-01-22 | 46409.0001
M-05 | Project closure | Closure | D-07 | [Owner 2] | 2027-02-26 |  |  | Not started | Final payment | 0 | Green | 2027-02-26 | 46444.0001
Formulas:
Effective date = IF([Milestone]="","",IF([Actual date]<>"",[Actual date],IF([Forecast date]<>"",[Forecast date],[Baseline date])))

## Dashboard
PROJECT DASHBOARD
[Project Name] ¦ Project manager: [Name] ¦ Status as at 29-Oct-2026
Timeline: 01-Sep-26 to 26-Feb-27 ¦ Time elapsed: 33%
Deliverables |  | Completed |  | Overdue (Red) |  | Average % complete |  | Milestones achieved
7 |  | 2 |  | 1 |  | 44.29% |  | 1 / 5
Deliverables by status |  |  |  | Deliverables by RAG
Status | Count | % of total |  | RAG | Deliverables | Milestones
Not started | 3 | 42.86% |  | Green | 3 | 3
In progress | 2 | 28.57% |  | Amber | 1 | 1
At risk | 0 | 0% |  | Red | 1 | 0
On hold | 0 | 0% |  | Complete | 2 | 1
Completed | 2 | 28.57% |  | On hold | 0 | 0
Cancelled | 0 | 0%
|  |  |  | Open deliverables due in next 30 days |  | 1
|  |  |  | Deliverables awaiting approval |  | 0
Progress by phase / workstream | [5 empty] | Next open milestones
Phase | Deliverables | Completed | Overdue | Avg % complete |  | Milestone | Date | Owner | RAG
Initiation | 1 | 1 | 0 | 100% |  | Baseline completed | 2026-11-06 | [Owner 3] | Amber
Planning | 2 | 1 | 1 | 85% |  | Equipment installed | 2026-11-20 | [Owner 4] | Green
Execution | 2 | 0 | 0 | 20% |  | Mid-term review | 2027-01-22 | [Owner 1] | Green
Monitoring | 1 | 0 | 0 | 0% |  | Project closure | 2027-02-26 | [Owner 2] | Green
Closure | 1 | 0 | 0 | 0%

## Timeline
DELIVERABLES TIMELINE (GANTT)
Weeks beginning Monday. Blue = planned; red = overdue; grey = completed; orange column = status date (29-Oct-26).
This sheet updates automatically from the Deliverables sheet – no data entry needed.
ID | Deliverable | Owner | Start | Due | Status | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22
D-01 | Project charter | [Owner 1] | 2026-09-01 | 2026-09-15 | Completed
D-02 | Stakeholder engagement plan | [Owner 2] | 2026-09-10 | 2026-09-30 | Completed
D-03 | Baseline survey report | [Owner 3] | 2026-09-21 | 2026-10-23 | In progress
D-04 | Procurement of equipment | [Owner 4] | 2026-10-05 | 2026-11-06 | In progress
D-05 | Training of field staff | [Owner 5] | 2026-11-16 | 2026-12-11 | Not started
D-06 | Mid-term progress report | [Owner 1] | 2026-12-14 | 2027-01-15 | Not started
D-07 | Final evaluation report | [Owner 3] | 2027-01-18 | 2027-02-19 | Not started